Iteration planning
What is it ?
  - A time-sequenced set of activities and tasks, with assigned people, containing task dependencies, for the iteration
  - a fine-grained plan.

---
Iteration planning template

---
Iterations in past
have
  - Slipped
  - Had a lot of bugs to be taken care of.
Result
  - Delivery of iterations not in time
  - Quality of deliverables not upto standards
  - Functionality delivered not aligned with business expectations
Root cause
  - Unclear requirements understanding.
  - Mismatched expectations with clients
  - Unclear understanding of all tasks to complete requirement

---
Iteration planning objectives
Developers
  - understand business requirements
    - Implication of requirements completely
  - Understand outcomes expected clearly
    - Create acceptance tests to articulate output
  - Create
    - Activities and tasks to realise the requirement
    - Estimate time for completion of all tasks
    - Assign ownership to tasks
Leads
  - Foresee and resolve issues, dependencies
  - Monitor and control deviations
  - Facilitate acceptance

---
Iteration planning objectives
QA
  - Understands business requirements
  - Validates team has understood requirements correctly
  - Validates team activities and test cases for correctness
  - Improves quality by
    - adding more test scenarios
    - Automating existing scenarios
  - Improves build output quality to customers
  - Improves customer experience
Customer and business analysts
  - Active participation, ownership in team activities
  - Course correct any issues in real time

---
Iteration planning objectives
Architects
  - Assess architectural correctness of solution
  - Help team to cater to non functional requirements
  - Improve quality and productivity
  - Product management
    - Manage release plan
    - Stakeholder interests

---
Iteration planning process
Business Analyst creates scope, requirements
A technology team member
  - Creates stories after breaking down requirements
  - Creates acceptance tests for each story
    - Reviews and finalises tests with QA and BA
  - Creates low level design for requirement
  - Creates tasks using low level design
  - Estimates tasks
    - Includes steps of doneness in estimates
A track lead
  - Aligns story along builds
  - Plans for acceptance and go live

---
Iteration planning process
QA
  - Reviews,modifies and get a sign off on acceptance test cases
    - Includes new tests for increasing test coverage
  - Automates last iteration stories

---
Iteration planning Deliverables
All stories, tasks identified, estimated and put in rally
All acceptance test cases signed off for all stories
Clearly defined timelines of story delivery w.r.t builds
Unforseen dependencies, risks mitigated
Dev-complete and Go-live dates published

---
What is a story
INVEST in Good Stories, and SMART Tasks :-)
  - http://xp123.com/xplor/xp0308/index.shtml
A good story
  - breaks down requirements to more manageable units
  - Help team collaborate and achieve requirements
e.g. Requirement: show customer portfolio on web
  - Stories
    - Show portfolio details as on date
    - Show portfolio summary as on date
    - Search transactions based on date range
    - Calculate return calculation for investment in single folio, scheme

---
What is an acceptance test case
Stories are abstract
Acceptance tests for a story
  - Define concrete outcomes
  - Bring developer, tester, client on same page
  - Cover all business scenarios applicable to a story
e.g. For portfolio on web requirement
Deepak should see a portfolio summary
  - Rs1,30,000 as CP
  - Rs. 1,00,000 as PV
Negative test cases
  - Prakash sees folio 9989921 for scheme SBI tax marked as error
  - Prakash's sees below in portfolio summary
    - Rs1,30,000 as CP
    - Rs. 1,00,000 as PV

---
Steps of doneness
Steps to be performed as part of development process to mark a story to complete.
http://sites.google.com/a/itrust.in/technology/Home/process/steps-of-doneness