## Red_Green_For_SALT
SOW Headings | Planned Tasks within SOW | Activities(Green - Can be achieved)(Red - Cannot be achieved) | Benefits (in Green)Benefits not achievable (in RED)
6.a BDD/TDD (Behaviour/Test Driven Development) implementation across Product Owner, Dev and Test functions | 1. Team training and implementation of BDD/TDD | 1. Team Training on BDD mapped to real implementation of process 2. Highlight responsibilities of BSM, QA and Dev 3. In-sprint practice of roles and responsibilities 5. Train the BSM with techniques to identify scenarios for any feature including: a. Feature injection b. Impact Mapping c. Purpose based Alligned model | 1. BDD Concept and and its outcomes 2. BDD as a process 3. Roles and Responsibilities of BSM, QA and Dev in team 4. Realization of Quality metrics 5. Since BSMs are in UK, working collaboratively write the stories in the BDD template is a challenge
| 2. Identification and implementation of technology solution cucumber, Jbehave etc. | 1. Introduced advanced reporting 2. Integration with MSTest Runner 3. Integration of Zephyr and Zapi to Jira4. Capturing requirements in BDD format5. Feature file driven coding, it's associated test cases and coding exit criteria 6. Feature file driven tests and workarounds | Story writing is done in UK and bringing maturity in the story writing process as per BDD will be a challenge
| 3. Implement 6.a.2 as part of ALM (application lifecycle management) | 1. Integrate in CI pipeline Unit Tests Static Tests Code Coverage Integration Tests Regression Tests Automated Test on UAT | All test automation suites are automated and made part of CI process
| 4. Maintenance and usage of test cases on Cucumber or any other identified tool for functional, regression and system test cases | 1. Tagging Regression, Smoke, E2E, Happy-Path, Integration and Unit optimized test execution cycle 2. For Robust and Maintainable framework, recommend best practices 3. Training on the best practices for scenario identification to BSM 4. Code Review and best practices | 1. Seperate job for automation suites are created and steamlined in process 2. Recommendations and suggestions within automation code to make more robust and maintainable 3. Guidelines for best practices within test automation
6.b Automation frameworks, tools and coverage - maturity assessment and orchestration (process, policies and tools) | 1. Identification & Implementation of tool based automation | Done as part of 6.a.2 1. Introduced advanced reporting 2. Integration with MSTest Runner 3. Integration of Zephyr and Zapi to Jira | Advance reporting and better debugging
| 2. Implement Feature toggles | Execution with respect to feature tags | Test suitest enabled to execute in different suites
6.c Left shift testing strategy and implementation | 1. Automated Unit, performance and security test implemented as part of CI process | 1. Create a Left Shift Strategy, get sign-off from Travelex 2. Showcase the Release cycle with Testing 3. Showcase the process with test in BDD 4. Showcase the phase wise activities of BDD implementation5. Automated test first approach 6. Feature file driven implementation 7. Executable specifications 8. Test reliable automation pipeline9. Left Shift of Performance and Security Testing | Feature file creation and scenario identification is delayed to test level rather than planningWith the existing team structure with more manuals, and delayed and reduced test automation, long release cycle, reduced unit and integration tests, we will be missing various attributes 1. Enhanced story writing 2. Ubiquitious language 3. Collaborative efforts 4. Automated reliable pipeline 5. Enabling ideal test pyramid 6. Executable scedifications 7. Automated UAT 8. Reduce rework
| 2. Successful execution of orchestrated test cycle meeting definition of done | 1. Strategize the branching strategy 2. Integrate test reports with CI CD and report links 3. Acknowledge with release cycle and its monitoring | Integration of QA cycles with DevOps
6.d Implementation of Quality Pyramid | 1. Automated scalability tests | 1. Entire tests automated in CI Pipeline2. Test Pyramid in shape Unit test > 70% Integration/API test > 20% UI Tests > 10% 3. Automated Living Documentation4. POC for Zephyr and ZAPI for jira automation | As per current state, where unit test is 3%, integration 5% and UI 50%, there by the test pyramid will remain as is
2. Automated UAT and feature acceptance test
3. Automated testing implemented using APIs and classes-level testing
4. Automated GUI testing required for releases – scope definition
6.e Test Data management | Define approaches to have test data segregation | Suggest approaches for data segregarion
6.f V&V for environment readiness, deployment and go live | 1. Automated CI process 2. Automated test execution – meeting scope and coverage 3. Provision environments – repeatable and reusable 4. Approval process, sign off criteria and gate checklists are automated through tools – Decision enablement for go-no go | 1. Plan of tests and their execution in CI Pipeline 2. Define threshold for failure 3. Completely automated test cycle 4. Automated sign off criteria bases on parameterized percentage 5. GO NO-GO decision by automated gates configuration | Entire process will be automated as part of CI pipeline with parameterized attributes to pass to higher environments