## QA WorkList Mapping to SOW
Planned Tasks - SOW Mapping
SOW Headings | Planned Tasks within SOW | To Do Activities | Deliverable
6.a BDD/TDD (Behaviour/Test Driven Development) implementation across Product Owner, Dev and Test functions | 1. Team training and implementation of BDD/TDD | 1. Team Training on BDD mapped to real implementation of process 2. Highlight responsibilities of BSM, QA and Dev 3. In-sprint practice of roles and responsibilities 5. Train the BSM with techniques to identify scenarios for any feature including: a. Feature injection b. Impact Mapping c. Purpose based Alligned model
| 2. Identification and implementation of technology solution cucumber, Jbehave etc. | 1. Introduced advanced reporting 2. Integration with MSTest Runner 3. Integration of Zephyr and Zapi to Jira 4. Capturing requirements in BDD format 5. Feature file driven coding, it's associated test cases and coding exit criteria 6. Feature file driven tests and workarounds | 1. BDD PPT 2. Cucumber Code base 3. BBD Implementation Strategy 4. BDD Future Reference
| 4. Maintenance and usage of test cases on Cucumber or any other identified tool for functional, regression and system test cases | 1. Tagging Regression, Smoke, E2E, Happy-Path, Integration and Unit optimized test execution cycle 2. For Robust and Maintainable framework, recommend best practices 3. Training on the best practices for scenario identification to BSM 4. Code Review mapped to impacts, practices for making framework more robust and maintainable
6.b Automation frameworks, tools and coverage - maturity assessment and orchestration (process, policies and tools) | 1. Identification & Implementation of tool based automation | Done as part of 6.a.2 1. Introduced advanced reporting 2. Integration with MSTest Runner 3. Integration of Zephyr and Zapi to Jira | 1. Traceability Matrix for TR 2. Code Review and Best Practices for SALT 3. Code Review and Best Practices for TR
| 2. Implement Feature toggles | Execution with respect to feature tags
6.c Left shift testing strategy and implementation | 1. Automated Unit, performance and security test implemented as part of CI process | 1. Create a Left Shift Strategy, get sign-off from Travelex 2. Showcase the Release cycle with Testing 3. Showcase the process with test in BDD 4. Showcase the phase wise activities of BDD implementation 5. Automated test first approach 6. Feature file driven implementation 7. Executable specifications 8. Test reliable automation pipeline Left Shift of Performance and Security Testing | Documentatoin for XRay - Test Management tool for Jira
| 2. Successful execution of orchestrated test cycle meeting definition of done | 1. Strategize the branching strategy 2. Integrate test reports with CI CD and report links 3. Acknowledge with release cycle and its monitoring | Utility for generating report and logs in SALT/TR
6.d Implementation of Quality Pyramid | 1. Automated scalability tests | 1. Entire tests automated in CI Pipeline 2. Test Pyramid in shape Unit test > 70% Integration/API test > 20% UI Tests > 10% 3. Automated Living Documentation 4. POC for Zephyr and ZAPI for jira automation | Performance: 1. JMeter Best Practices 2. Performance Test Plan Template 3. Performance Testing Metrics 4. JMeter - Real Time Results using Grafana and Influx DB 5. Performance Testing Framework 6. Performance Code Review and Best Practices
2. Automated UAT and feature acceptance test
3. Automated testing implemented using APIs and classes-level testing
4. Automated GUI testing required for releases – scope definition
6.e Test Data management | Define approaches to have test data segregation | Suggest approaches for data segregarion | 1. SALT Test strategy document
6.f V&V for environment readiness, deployment and go live | 1. Automated CI process 2. Automated test execution – meeting scope and coverage 3. Provision environments – repeatable and reusable 4. Approval process, sign off criteria and gate checklists are automated through tools – Decision enablement for go-no go | 1. Plan of tests and their execution in CI Pipeline 2. Define threshold for failure 3. Completely automated test cycle 4. Automated sign off criteria bases on parameterized percentage 5. GO NO-GO decision by automated gates configuration

## Sheet7
S No. | SOW Activity | Track | Tasks accomplished | Tasks Blocked/Not-done | Deliverable | SALT Phase | SALT Status | Description
6.a | BDD/TDD (Behaviour/Test Driven development) implementation across Product Owner, Dev and Test functions
6.a.1 | Team Training of BDD | TA | 1. Team training on BDD 2. Team training on Cucumber 3. Highlight responsibilities of BSM, QA and Dev 4. In-sprint practice of roles and responsibilities 5. Train the BSM with techniques to identify scenarios for any feature including: a. Feature injection b. Impact Mapping c. Purpose based Alligned model | BDD Implementation coaching for SALT | 1. BDD PPT 2. Cucumber Code base 3. BBD Implementation Strategy 4. BDD Future Reference | Phase 2 | Done
6.a.2 | Identification and implementation of technology solution cucumber, jbehave etc | TA | 1. Introduced Pretty Reports in Java Framework 2. Introduced advanced reports in SALT/TR 3. Implemetation of MS Test in SALT/TR | Implementation of parallel test execution in SALT |  | Phase 2 | Done
6.a.3 | Implement 6.a.2 as part of ALM (application lifecycle management) | TA | Done as part of 6.c.1 |  |  | Phase 3 | Planned | Dependent on CI and Environments
6.a.4 | Maintenance and usage test cases on Cucumber or any other identified tool for functional, regression and system test cases | TA | 1. Implemented tagging for traceability 2. Refactor code for living documentation and maintainability 3. Code Review for SALT/TR 4. Coding Best Practices for SALT/TR |  | 1. Traceability Matrix for TR 2. Code Review and Best Practices for SALT 3. Code Review and Best Practices for TR | Phase 2 | WIP | Shailendra, Code Review
6.b | Automation frameworks, tools and coverage - maturity assessment and orchestration (processes, policies and tools)
6.b.1 | Identification and implementation of tool based automation | TA | 1. Identification on Test Management tool - Zephyr/Xray for Jira | Implementation of XRay for Jira Test Management Tool | Documentatoin for XRay - Test Management tool for Jira | Phase 2 | WIP | Xray
6.b.2 | Implement feature toggles | TA | 1. Enabled test automation for execution from command line in SALT/TR |  | Utility for generating report and logs in SALT/TR | Phase 2 | Done
6.c | Left shift testing strategy and implementation
6.c.1 | Automated unit, performance and security test implemented as part of CI process | TA | Performance testing for SALT/TR Security Testing for SALT/TR |  | Performance: 1. JMeter Best Practices 2. Performance Test Plan Template 3. Performance Testing Metrics 4. JMeter - Real Time Results using Grafana and Influx DB 5. Performance Testing Framework 6. Performance Code Review and Best Practices | Phase 3 | Planned
6.c.2 | Successful execution of orchestrated test cycle meeting definition of done | TA | Automated tests in CD pipeline for SALT/TR 1. Regression tests 2. Smoke Tests 3. Happy Path4. Performance Test 5. Security Test |  |  | Phase 3 | Planned | CI Pipeline
6.d | Implementation of Quality Pyramid
6.d.1 | Automated scalability tests | TA | 1. Paired with team and showcased insprint Unit tests writing 2. Paired with BA's identifying scenarios 3. Paired with team and shohwcased automating scenarios 4. Showcased quality pyramid and its distribution in automation pipeline 5. Strategy and implementation of test automation in SALT |  | 1. SALT Test strategy document | Phase 3 | Planned
6.d.2 | Automated UAT and feature acceptance test | TA |  |  |  | Phase 3 | Blocked
6.d.3.1 | Automated testing implemented using APIs | TA |  |  |  | Phase 3 | Done
6.d.3.2 | Automated testing implemented using classes-level testing | UT |  |  |  | Phase 3 | Done
6.d.4 | Automated GUI testing required for releases - scope definition | TA |  |  |  | Phase 3 | Planned
6.e | Test Data Management
6.e.1 | Define approaches to test data segregation | TA | Suggested approaches for test data segregation |  |  | Phase 2 | Done
6.f | V&V environment readiness, deployment & go-live
6.f.1 | Automated CI Process | Devops | Taken care by DevOps |  |  | Phase 4 | Planned
6.f.2 | Automated test execution - meeting scope & coverage | TA |  |  |  | Phase 2 | Planned | Xray - Integration with Specflow
6.f.3 | Provision environments - repeatable and reusable | Devops |  |  |  | Phase 5 | Planned
6.f.4 | Approval process, sign off criteria and gate checklists are automated through tools - Decision enablement for Go-no-go | TA |  |  |  | Phase 5 | Planned

## SOW_QA_Tasks
S No. | SOW Activity | Track | Tasks accomplished | Tasks Blocked/Not-done | Deliverable | SALT Phase | SALT Status | Description
6.a | BDD/TDD (Behaviour/Test Driven development) implementation across Product Owner, Dev and Test functions
6.a.1 | Team Training of BDD | TA | 1. Team training on BDD 2. Team training on Cucumber 3. Highlight responsibilities of BSM, QA and Dev 4. In-sprint practice of roles and responsibilities 5. Train the BSM with techniques to identify scenarios for any feature including: a. Feature injection b. Impact Mapping c. Purpose based Alligned model | BDD Implementation coaching for SALT | 1. BDD PPT 2. Cucumber Code base 3. BBD Implementation Strategy 4. BDD Future Reference | Phase 2 | Done
6.a.2 | Identification and implementation of technology solution cucumber, jbehave etc | TA | 1. Introduced Pretty Reports in Java Framework 2. Introduced advanced reports in SALT/TR 3. Implemetation of MS Test in SALT/TR | Implementation of parallel test execution in SALT |  | Phase 2 | Done
6.a.3 | Implement 6.a.2 as part of ALM (application lifecycle management) | TA | Done as part of 6.c.1 |  |  | Phase 3 | Planned | Dependent on CI and Environments
6.a.4 | Maintenance and usage test cases on Cucumber or any other identified tool for functional, regression and system test cases | TA | 1. Implemented tagging for traceability 2. Refactor code for living documentation and maintainability 3. Code Review for SALT/TR 4. Coding Best Practices for SALT/TR |  | 1. Traceability Matrix for TR 2. Code Review and Best Practices for SALT 3. Code Review and Best Practices for TR | Phase 2 | WIP | Shailendra, Code Review
6.b | Automation frameworks, tools and coverage - maturity assessment and orchestration (processes, policies and tools)
6.b.1 | Identification and implementation of tool based automation | TA | 1. Identification on Test Management tool - Zephyr/Xray for Jira | Implementation of XRay for Jira Test Management Tool | Documentatoin for XRay - Test Management tool for Jira | Phase 2 | WIP | Xray
6.b.2 | Implement feature toggles | TA | 1. Enabled test automation for execution from command line in SALT/TR |  | Utility for generating report and logs in SALT/TR | Phase 2 | Done
6.c | Left shift testing strategy and implementation
6.c.1 | Automated unit, performance and security test implemented as part of CI process | TA | Performance testing for SALT/TR Security Testing for SALT/TR |  | Performance: 1. JMeter Best Practices 2. Performance Test Plan Template 3. Performance Testing Metrics 4. JMeter - Real Time Results using Grafana and Influx DB 5. Performance Testing Framework 6. Performance Code Review and Best Practices | Phase 3 | Planned
6.c.2 | Successful execution of orchestrated test cycle meeting definition of done | TA | Automated tests in CD pipeline for SALT/TR 1. Regression tests 2. Smoke Tests 3. Happy Path 4. Performance Test 5. Security Test |  |  | Phase 3 | Planned | CI Pipeline
6.d | Implementation of Quality Pyramid
6.d.1 | Automated scalability tests | TA | 1. Paired with team and showcased insprint Unit tests writing 2. Paired with BA's identifying scenarios 3. Paired with team and shohwcased automating scenarios 4. Showcased quality pyramid and its distribution in automation pipeline 5. Strategy and implementation of test automation in SALT |  | 1. SALT Test strategy document | Phase 3 | Planned
6.d.2 | Automated UAT and feature acceptance test | TA |  |  |  | Phase 3 | Blocked
6.d.3.1 | Automated testing implemented using APIs | TA |  |  |  | Phase 3 | Done
6.d.3.2 | Automated testing implemented using classes-level testing | UT |  |  |  | Phase 3 | Done
6.d.4 | Automated GUI testing required for releases - scope definition | TA |  |  |  | Phase 3 | Planned
6.e | Test Data Management
6.e.1 | Define approaches to test data segregation | TA | Suggested approaches for test data segregation |  |  | Phase 2 | Done
6.f | V&V environment readiness, deployment & go-live
6.f.1 | Automated CI Process | Devops | Taken care by DevOps |  |  | Phase 4 | Planned
6.f.2 | Automated test execution - meeting scope & coverage | TA |  |  |  | Phase 2 | Planned | Xray - Integration with Specflow
6.f.3 | Provision environments - repeatable and reusable | Devops |  |  |  | Phase 5 | Planned
6.f.4 | Approval process, sign off criteria and gate checklists are automated through tools - Decision enablement for Go-no-go | TA |  |  |  | Phase 5 | Planned

## QA BDD Implementation for SALT
SOW Headings | Planned Tasks within SOW | To Do Activities [As part of BDD] | Can be done? | Impact | Benefit
6.a BDD/TDD (Behaviour/Test Driven Development) implementation across Product Owner, Dev and Test functions | 1. Team training and implementation of BDD/TDD | 1. Team Training on BDD mapped to real implementation of process 2. Highlight responsibilities of BA, QA and Dev 3. Create a test strategy for BDD implementation and get a sign off from Travelex 4. Gap Analysis for Tech Refresh for BDD implementation 5. Acknowledge the BA with techniques to identify scenarios for any feature including: Feature injection Impact Mapping Purpose based Alligned model | Yes |  | BDD can be followed as process which outcomes: 1. More business knowledge to team 2. More collaboration, increased outputs 3. Faster delivery 4. Enhanced story writing minimizing rework
| 2. Identification and implementation of technology solution cucumber, Jbehave etc. |  | N/A
| 3. Implement 6.a.2 as part of ALM (application lifecycle management) | 1. Integrate in CI pipeline Unit Tests Static Tests Code Coverage Integration Tests Regression Tests Automated Test on UAT | Partilly | Test pipeline will not be reliable because: 1. Not all modules are automated 2. No or less unit tests written 3. No or less inegration tests written 4. In-sprint automation is missing 5. BA verification on UAT still exists
| 4. Maintenance and usage of test cases on Cucumber or any other identified tool for functional, regression and system test cases | 1. Tagging Regression, Smoke, E2E, Happy-Path, Integration and Unit optimized test execution cycle 2. For Robust and Maintainable framework, recommend best practices 3. Training on the best practices for scenario identification to BA 4. Code Review and best practices | Yes |  | Living documentation can be created to some extends
6.b Automation frameworks, tools and coverage - maturity assessment and orchestration (process, policies and tools) | 1. Identification & Implementation of tool based automation |  | Done
| 2. Implement Feature toggles | Execution with respect to feature tags | Done
6.c Left shift testing strategy and implementation | 1. Automated Unit, performance and security test implemented as part of CI process | 1. Create a Left Shift Strategy, get sign-off from Travelex 2. Showcase and implement the Release cycle with Testing 3. Showcase and implement the process with test in BDD 4. Showcase and implement the phase wise activities of BDD implementation 5. Implement the LeftShift Strategy 6. Integrate in CI pipeline Unit Tests Static Tests Code Coverage Integration Tests Regression Tests BA Automated Test on UAT | Partially | Even after implementinf Left Shift automation bugs will be captured at later stage
| 2. Successful execution of orchestrated test cycle meeting definition of done | 1. Strategize the branching strategy 2. Integrate test reports with CI CD and report links 3. Acknowledge with release cycle and its monitoring | Yes |  | Entire process is automated with all the tests performed in planned release cycle
6.d Implementation of Quality Pyramid | 1. Automated scalability tests | 1. Entire tests automated in CI Pipeline 2. Test Pyramid in shape Unit test > 70% Integration/API test > 20% UI Tests > 10% | No | Test Pyramid will remain inverted
2. Automated UAT and feature acceptance test
3. Automated testing implemented using APIs and classes-level testing
4. Automated GUI testing required for releases – scope definition
6.e Test Data management | Define approaches to have test data segregation |  | N/A
6.f V&V for environment readiness, deployment and go live | 1. Automated CI process 2. Automated test execution – meeting scope and coverage 3. Provision environments – repeatable and reusable 4. Approval process, sign off criteria and gate checklists are automated through tools – Decision enablement for go-no go | 1. Plan of tests and their execution in CI Pipeline 2. Define threshold for failure 3. Completely automated test cycle 4. Automated sign off criteria bases on parameterized percentage 5. GO NO-GO decision by automated gates configuration | Yes |  | Automated gates define whether build should process to next environment or nor

## SOW Titles
S No. | SOW Activity | Track | SALT Phase | SALT Status | T R Phase | T R Status | Remarks
3.e.2 | Implement tools to be used for identifying unit level performance and security issues (Left shift test model) | TA | Phase 3 |  | Phase 3
6.a.1 | Team Training of BDD | TA | Phase 2 | Done | Phase 2 | Done | Moved from original phase-2 to 3 agreed among Tushar , Pranav, Darshit & Gajanan ( 25th Oct )
6.a.2 | Identification and implementation of technology solution cucumber, jbehave etc | TA | Phase 2 | Done | Phase 2 | Done | No changes required
6.a.3 | Implement 6.a.2 as part of ALM (application lifecycle management) | TA | Phase 3 | Blocked | Phase 3 | Planned | Dependent on CI and Environments
6.a.4 | Maintenance and usage test cases on Cucumber or any other identified tool for functional, regression and system test cases | TA | Phase 2 | Blocked | Phase 2 | Planned
6.b.1 | Identification and implementation of tool based automation | TA | Phase 2 | Planned | Phase 2 | Planned | POC for Specflow reporting using MSTest Runner for SALT And TechRefresh Zephyr - PendingPOC for Specflow reporting using MSTest Runner for SALT And TechRefresh Zephyr - Pending
6.b.2 | Implement feature toggles | TA | Phase 2 | Done | Phase 2 | Done
6.c.1 | Automated unit, performance and security test implemented as part of CI process | TA | Phase 2 | Planned | Phase 2 | Planned
6.c.2 | Successful execution of orchestrated test cycle meeting definition of done | TA | Phase 3 | Planned | Phase 3 | Planned | Reporting using NUnit/MSTest. Dashboard to be available to PO
6.d.1 | Automated scalability tests | TA | Phase 3 | Planned | Phase 3 | Planned | Moved from original phase-2 to 3 agreed among Tushar , Pranav, Darshit & Gajanan ( 25th Oct )
6.d.2 | Automated UAT and feature acceptance test | TA | Phase 3 | Blocked | Phase 3 | Blocked | Blocker from business about agreeing it as part of Sprint
6.d.3.1 | Automated testing implemented using APIs | TA | Phase 2 | Done | Phase 2 | Done
6.d.4 | Automated GUI testing required for releases - scope definition | TA | Phase 3 | Planned | Phase 3 | Planned | Release yet to finish. Post release completion this should be done. Moved from original phase-2 to 3 agreed among Tushar , Pranav, Darshit & Gajanan ( 25th Oct )
6.e.1 | Define approaches to test data segregation | TA | Phase 2 | Done | Phase 2 | Done
6.f.2 | Automated test execution - meeting scope & coverage | TA | Phase 2 | Planned | Phase 2 | Planned
6.f.4 | Approval process, sign off criteria and gate checklists are automated through tools - Decision enablement for Go-no-go | TA | Phase 5 | Planned | Phase 5 | Planned

## Date Wise Work
Date | Task Accomplished | Open Queries | Tasks Planned
2016-11-23 | Training on BDD to entire Tech Refresh Team [Attendees: Tech Refresh Team]
2016-11-23 | Meeting within Manjeet for discussion of process, tool and technologies
Tech Refresh BDD Implementation Strategy Review [Attendees: Tushar, Naina, Kamlesh]
2016-11-23 | Joined team preplanning meeting to understand stories
2016-11-24 | BDD Training to BA in Tech Refresh [Attendees: Mohit and Gaurav]
2016-11-24 | Setting up JIRA cloud for Zephyr POC
2016-11-24 | Provide Travelex team for solutions and best practices for performance testing
2016-11-24 | Joined team planning meating with onsite folks
2016-11-24 | Joined team re-estimation meeting with Pranav for best practices
2016-11-25 | Installing Zephry and Zapi to cloud
2016-11-25 | Scope analysis with team for BDD implementation [Attendees: Tech Refresh team + Darshit]
2016-11-25 | TechRefresh Team BDD implementation strategy walkthrough [Attendees: Tech Refresh team + Darshit]
2016-11-25 | Select 2 in-sprint demo stories for BDD implementation
2016-11-28 | Write a feature file for CSR-1887 for BDD showcase
2016-11-28 | Write a feature file for CSR-1891 for BDD showcase
2016-11-28 | Hit API using ZAPI on cloud
2016-11-28 | SALT- Impact analysis - Shared initial draft with Shankar and team
2016-11-28 | Acknowledge BA with format of feature file in story writing [Attendees: Mohit, Gaurav, Gajanan, Pranav]
2016-11-29 | BDD Training to QA in Tech Refresh [Attendees: Suraj, Monica and Manual testing boy]
2016-11-29 | Attended call with Mandeep for performance testing
2016-11-29 | Follow up for questionnaire for performance test automation
2016-11-29 | BDD Training to Dev in Tech Refresh [Attendees: William, Praveen, Karan and Shruti]
2016-11-29 | Session with BA for story understanding
2016-11-29 | Impact vs Benefits mapping for BDD implementation in SALT
2016-11-30 | Attended call with Shankar for Impact analysis for BDD implementsation
2016-11-30 | Updated review comments by Shankar in the same sheet
2016-11-30 | Met mohit BA for story grooming
2016-11-30 | Follow up in emails for Security and Performance testing
2016-11-30 | Groomed each story within sprint and strategized to write in BDD format
2016-12-01 | Update impact analysis document
2016-12-01 | SOW discussion with Tushar and Darshit[didnt completed][Stuck with test management tool]
2016-12-01 | Follow up with Mohit for Open questions
2016-12-01 | Write all stories before grooming session with team on Friday
2016-12-02 | Integration of Static tests, unit tests, code coverage and API test in CI pipeline
2016-12-02 | Backlog grooming session in BDD with Tech Refresh team
2016-12-02 | Test Code Review for Tech Refresh
2016-12-02 | Tagging regression cases - @External and @Internal tags
2016-12-05 | Best Practices document for tech refresh
2016-12-05 | Scenario identification for next sprint stories with Manual team
2016-12-05 | Scenario identification for next sprint stories with BA
2016-12-05 | Tech Refresh Code Review
2016-12-06 | Automation guidance for Manual tests [Attendees: Sujaj, Manish, Monica, +1]
2016-12-06 | BA to acknowledge for Roles and Responsibilities [Attendees: Mohit and Gaurav]
2016-12-07 | Best Practices document for tech refresh
2016-12-07 | Coding snippets mapped to best practices
Automation framework acknowledgement for Manual tests
2016-12-07 | XRay environment setup
2016-12-07 | Solve issue in command line automation execution for all suites
2016-12-07 | advance report integration in Tech-Refresh and SALT
2016-12-08 | Explore XRay Manual and automated exporting features
2016-12-08 | Explore XRay Manual and automated importing results
2016-12-08 | Showcase test manament tool to Travelex management
2016-12-08 | Attended meeting with Security team for roadmap [Attendees: Chandra, Priyanka, Pranav]
2016-12-08 | Attended call with Manjeet and Pranav for Performance
2016-12-08 | BA for grooming stories
2016-12-08 | Hosted XRay locally for travelex to explore more
2016-12-09
2016-12-09 | BA grooming session
2016-12-09 | Manual Scenario Identificatoin
2016-12-09 | BA Scenario Walkthrough
BA story grooming after grooming session with team
Manual team session 2
BDD in Actions presentation with team
Answer queries for BDD implementation
Team walkthrough with Code Review
Identify Limitations of XRay for tool finalization
Team walkthrough with Best Practices
Follow up with performance testing with Manjeet - Identify all tasks Data Monitoring tool - MySQLDB Framework for performance testing Left Shift strategy for Performance Integration to bitbucket- performance code Process acknowledgement
Setup Performance JMeter code
Code review for SALT
Best practices for SALT
Demonstration of Code Review process in Test Automation
Implement Tagging
Review Best Practices for SALT
Retrospective for BDD story
BA training for scenario writing for next print stories
Grooming session 2 with Team
Review Code Review comments for SALT
Integrating one test suite of TR or SALT in CI pipeline
Strategy for moving in-sprint tasks to regression suite
Review Strategy for SALT regression
Documentation for XRAY for Jira
Documentation for Tech-Refresh Forward and Backward Traceability
Integration of Functional automation tests and regression test in CI pipeline
4. Integrate Tech Refresh test automation code in CI pipeline
Integrate API framework in CI/CD
Create executable for API framework
Share all documents together created anytime - BDD Strategy, ppt, code, book, phase wise implementation
Share Code review and Best Practices documents